## Event RA
Risk Assessment
Event |  |  | Junior Inter Regional Regatta |  |  | Date: |  | 23.4.2022
Author |  |  | Joanna Cotgrove |  |  | Rev: |  | 1
No: | Hazard | Reduce probability a Hazard causing a Hazardous Event |  | Hazardous Event | Reduce the Severity of Harm |  | Harm | Severity (1-5) | Probability (A-E) | Level of Risk (L/M/S/I) | Action Owners
|  | Barriers | Action to maintain barriers |  | Controls | Action to maintain controls |  |  |  |  | Event Committee | Event RSA | Safety Boat Drivers | Control Commissions | other
Water
1 | Racing | Coaches and crews to have read instructions to competitors and coaches to have taught athletes how to steer | Many regions select crews through a competitive selection process to ensure best candidates from the region therefore more likely to have these skills | Collision between crews racing in the same race | An umpire's launch to follow each race. | 5 Umpires launches on water which allows for plenty of time between races and a proper suppleant, safety boats positioned at start, finish and mid course | Damage to boats, cold water immersion or minor injury | 1 | C | Low | X |  | X
1 | Racing | Crews follow the circulation plan Crews keep a good lookout | Brief competitors to follow the circulation plan and keep a good lookout Coaches to have taught athletes how to steer | Collision between crews racing in the same race | Rescue with launch Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | 5 Umpires launches on water which allows for plenty of time between races and a proper suppleant, safety boats positioned at relevant points Umpire's launch to follow each race Provide somewhere warm for anyone suffering from cold | Damage to boats, cold water immersion or minor injury | 1 | C | Low | X |  | X
2 | Racing and crews rowing to the start in adjoining lanes | Coaches and competitors to have read the safety instructions, instructions to competitors and circulation patterns, marshalls in the access lane to assist competitors | Circulation pattern to be displayed in Control Commission | Collisions between a boat going to the start and a boat racing | Umpire's launch to follow each race, marshalls to be positions in the access lane, fully equipped safety launches | Sufficient safety cover, control commission checks | Damage to boats, cold water immersion or minor injury | 3 | C | Moderate | X |  | X | X
2 | Racing and crews rowing to the start in adjoining lanes | Crews follow the circulation plan Crews keep a good lookout Marshals to direct crews | Circulation pattern to be displayed in Control Commission Brief competitors to follow circulation plan and keep a good lookout Sufficient marshals correctly positioned | Collisions between a boat going to the start and a boat racing | Rescue with launch Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Sufficient safety cover, control commission checks Umpire's launch to follow each race Provide somewhere warm for anyone suffering from cold Provide sufficient first aid cover | Damage to boats, cold water immersion or minor injury | 3 | C | Moderate | X |  | X | X
3 | Racing | Crews to be at a competent level to race, conditions on the day to be assessed | Crews are selected through a selection process within region which should ensure a higher standard of competence | Capsize during a race | Umpire's launch to follow each race, safety launches to be positioned on the course and properly equipped. | Sufficient safety cover, coxed boats to be checked for life jackets, general competence of crew and ability to recover assessed through selection process | Submersion in cold water | 2 | A | Low | X |  | X | X | X
3 | Racing | Crews to be at a competent level to race, conditions on the day to be assessed | Crews are selected through a selection process within region which should ensure a higher standard of competence | Capsize during a race | Rescue with launch Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital | Sufficient safety cover, coxed boats to be checked for life jackets, general competence of crew and ability to recover assessed through selection process Umpire's launch to follow each race Provide somewhere warm for anyone suffering from cold Provide sufficient first aid cover | Submersion in cold water | 2 | A | Low | X |  | X | X | X
4 | Presentation Raft/Boating raft on Country park | Crews prohibited from using lane 0, all crews to be aware of circulation pattern and instructions to competitors | Crews aware of circulation pattern, crews and coaches to be provided with competitors instructions ahead of time, large buoy to be placed at end of presentation raft | Collisions with presentation raft or Country park boating raft | Umpire on Country Park station finish umpires to be appropriately briefed later in the day, ceremonial umpire in use and each race to be followed by an umpire | Sufficient safety cover, coxed boats to be checked for life jackets, general competence of crew and ability to recover assessed through selection process | Collision with hard object, damage to boats, injuries to competitors, capsize and submersion in cold water | 3 | C | Moderate | X |  | X | X | X
4 | Presentation Raft/Boating raft on Country park |  | Crews aware of circulation pattern Crews and coaches to be provided with competitors instructions ahead of time, large buoy to be placed at end of presentation raft Brief competitors to follow circulation plan and keep a good lookout Sufficient marshals correctly positioned | Collisions with presentation raft or Country park boating raft | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Umpire on Country Park station finish umpires to be appropriately briefed later in the day, ceremonial umpire in use and each race to be followed by an umpire Sufficient safety cover, coxed boats to be checked for life jackets, general competence of crew and ability to recover assessed through selection process Provide sufficient throwlines | Collision with hard object, damage to boats, injuries to competitors, capsize and submersion in cold water | 3 | C | Moderate | X |  | X | X | X
5 | Crews follow the circulation plan Crews keep a good lookout Marshals to direct crews | Crews advised that they will need to have licences for the Trent, and must read the river Trent circulation instructions | Crews advised to inform the regatta of their intentions to boat on the Trent | Incident on the Trent/ capsize or injury to competitor | First aid facilities to be provided on site |  | Minor injury, cold water immersion, minor damage to boats | 1 | B | Low |  |  |  |  | X
5 | Crews practising on the Trent | Only crews with liscences to practice on the trent | Only crews with licences to boat on the Trent | Incident on the Trent/ capsize or injury to competitor | Administer first aid Slowly warm anyone suffering from cold Take to hospital f necessary | First aid facilities to be provided on site | Minor injury, cold water immersion, minor damage to boats | 1 | B | Low |  |  |  |  | X
6 | congestion of crews on the water in the finish and boating areas | Race Committee to monitor conditions, crews to have read the circulation pattern in advance of the event | ensure that there are sufficient marshalls in both the incoming and outgoing pontoons, megaphones to be provided to marshalls | Strong tail wind blowing crews that have finished onto the de-boating pontoons or onto other crews boating | Safety provision in the finish area, control commission to be provided with throw lines, all umpires to be briefed on summoning safety and first aid | briefing on safety and first aid | minor injury, cold water immersion and minor damage to boats | 2 | D | Moderate | X | X | X | X | X
6 | congestion of crews on the water in the finish and boating areas | Crews to follow the circulation pattern Marshalls to instruct crews Suspend boating and racing, if necessary, until area is cleared | ensure that there are sufficient marshalls in both the incoming and outgoing pontoons, megaphones to be provided to marshalls Race Committee to monitor conditions, Brief crews to follow the circulation plan | Strong tail wind blowing crews that have finished onto the de-boating pontoons or onto other crews boating | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital | briefing on safety and first aid Safety provision in the finish area, control commission to be provided with throw lines, all umpires to be briefed on summoning safety and first aid | minor injury, cold water immersion and minor damage to boats | 2 | D | Moderate | X | X | X | X | X
7 | crews on water moving in different directions | Ceremonial marshal to be used, crews to be briefed when boating for finals | appropriate briefing of ceremonial marshal, appropriate monitoring of weather conditions | Collision between crews waiting for prizegiving and crews finishing racing | throw lines and megaphone to be provided to ceremonial marshal | briefing on appropriate summoning of first aid | minor injury and minor boat damage | 1 | C | Low | X |  |  |  | X
7 | crews on water moving in different directions | Crews to follow circulation plan and marshals instructions Marshals to direct crews | appropriate briefing of ceremonial marshal, appropriate monitoring of weather conditions Ceremonial marshal to be used, crews to be briefed when boating for finals | Collision between crews waiting for prizegiving and crews finishing racing | Rescue with launch or throwline Administer first aid Slowly warm anyone suffering from cold Take to hospital f necessary | briefing on appropriate summoning of first aid throw lines and megaphone to be provided to ceremonial marshal | minor injury and minor boat damage | 1 | C | Low | X |  |  |  | X
Weather
1 | Number of Boats on water | Race Committee and Safety advisor to consider conditions, competitors to be advised as to circulation patterns, crews to be competent due to circulation patterns | Continual monitoring of weather conditions in the context of competence of the crews | Boat in lane 7 blown into path of racing | An umpire to follow each race and safety cover to be positioned appropriately on the course | Briefing of umpires and safety cover by Race Committee Chari and Safety advisor | Cold water immersion and risk of hypothermia, and risk of minor injury and boat damage | 2 | D | Moderate | X | X | X | X | X
1 | Number of Boats on water | Crews to take account of weather conditions and take extra care with steering and keep a good lookout | Continual monitoring of weather conditions in the context of competence of the crews, consider the circumstances in light of the abandonment plan Race Committee and Safety advisor to consider conditions, competitors to be advised as to circulation patterns, crews to be competent due to circulation patterns Brief crews on the effect of weather conditions | Boat in lane 7 blown into path of racing | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Briefing of umpires and safety cover by Race Committee Chari and Safety advisor An umpire to follow each race and safety cover to be positioned appropriately on the course | Cold water immersion and risk of hypothermia, and risk of minor injury and boat damage | 2 | D | Moderate | X | X | X | X | X
2 | Sudden Bad weather causing intolerable or unrowable conditions | Race Committee Chair and Safety advisor to monitor weather conditions and to make early decisions, boats to be directed by umpires and safety crews to sheltered parts of the water, and got off water as quickly as possible |  | Swamping or capsize | Crews to be directed to sheltered locations on the course, or removed if at all possible, fully equipped safety launches | Umpires to be briefed on methods to maintain radio contact with umpires and audio contact with crews in advance of racing | Cold water immersion and risk of hypothermia, and risk of minor injury | 2 | D | Moderate | X | X | X | X | X
2 | Sudden Bad weather causing intolerable or unrowable conditions | Suspend racing Stop boats from going afloat Direct crews to sheltered water Get boats off the water as quickly as possible | Race Committee Chair and Safety advisor to monitor weather conditions and to make early decisions Brief Officials and competitors | Swamping or capsize | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Provide working radios, ensure officials know how to use them and the correct radio procedure Provide sufficient safety cover Provide adequate first aid cover | Cold water immersion and risk of hypothermia, and risk of minor injury | 2 | D | Moderate | X | X | X | X | X
3 | Severe Storm accompanied by thunder and lightening during racing | Safety advisor and RCC to monitor weather in advance of event and throughout the day, competitors to receive thunder and lighting abandonment planning, PA utilised to orchestrate abandonment plan | Continual monitoring of weather conditions, 30/30 plan to be implemented in the event of a storm, any variation from 30/30 rule to be agreed by race committee and safety advisor in conjunction with event chair | Competitor or official struck by lightening | Racing to be stopped and crews to be removed from the water as soon as possible, officials to clear the course as quickly as possible, first aid provision available on site, and casualites to be retrieved from the course and given first aid or taken to hospitl as appropriate | provision for removal of crews to hospital if necessary | electrical burns and shock | 4 | B | Moderate | X | X | X | X | X
3 | Severe Storm accompanied by thunder and lightening during racing | Suspend racing and boating Get all boats off the water as quickly as possible Implement the 30/30 plan | Safety advisor and RCC to monitor weather in advance of event and throughout the day, competitors to receive thunder and lighting abandonment planning, PA utilised to orchestrate abandonment plan Continual monitoring of weather conditions, 30/30 plan to be implemented in the event of a storm, any variation from 30/30 rule to be agreed by race committee and safety advisor in conjunction with event chair Brief crews and officials | Competitor or official struck by lightning | Administer first aid Evacuate to hospital | provision for removal of crews to hospital if necessary Provide adequate first aid | electrical burns and shock | 4 | B | Moderate | X | X | X | X | X
4 | Hot Weather | athletes to be advised to take water afloat with them and to ensure that they are appropriately dressed and wearing sun cream | control commission to advise athletes whilst boating | sunburn, heat stroke or heat exhaustion | First aid facilities available | umpires and marshalls to be briefed on summoning first aid facilities | sunburn, heatstroke or heat exhaustion | 2 | D | Moderate | X | X | X
4 | Hot Weather | Competitors to carry water and wear appropriate clothing | control commission to advise athletes whilst boating athletes to be advised to take water afloat with them and to ensure that they are appropriately dressed and wearing sun cream Ensure sufficient supplies of water are available | sunburn, heat stroke or heat exhaustion or dehydration | Administer first aid Cool shower | umpires and marshalls to be briefed on summoning first aid facilities Provide adequate first aid cover Provide shelter from sun Provide cool showers | sunburn, heatstroke or heat exhaustion | 2 | D | Moderate | X | X | X
5 | Cold weather and rain | Competitors to boat in appropriate clothing with plenthy of layers including waterproof layer | control commission to advise athletes whilst boating | hypothermia and injury caused by exposure to cold conditions over time | Administer first aid and where necessary, provison of room for affected competitors to warm up inside | Umpires and marshals to be briefed on summoning first aid, provision of indooe space and summoning help from coaches | hypothermia and cold | 2 | D | Moderate | X | X |  | X
6 | [9 empty] | #N/A
7 | [9 empty] | #N/A
Other water users
1 | Officials, marshalls, launch drivers and first aider not aware of safety procedures | Briefing for all volunteers | Monitoring of procedures by race and organising committee throughout the day | delay or inappropriate course of action in response to a situation |  |  | immersion in cold water, injury or boat damage | 3 | C | Moderate | X | X
1 | Officials, marshalls, launch drivers and first aider not aware of safety procedures | Check that each volunteer has read and understood the safety procedures | Monitoring of procedures by race and organising committee throughout the day Briefing for all volunteers Provide concise instruction sheets to volunteers | delay or inappropriate course of action in response to a situation | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Provide working radios, ensure officials know how to use them and the correct radio procedure Provide sufficient safety cover Provide adequate first aid cover | immersion in cold water, injury or boat damage | 3 | C | Moderate | X | X
2 | floating water based installations with requirement of people on then | number of people on water based installation to be limited |  | person falling off intermediate start or stakeboat | all stakeboat personnel and umpires to wear buoyancy aids/lifejackets | safety boats and first aid provision to be available in the start area and marshalls and umpires to be briefed on summoning help | immersion in cold water | 1 | B | Low | X | X | X
2 | floating water based installations with requirement of people on then | Ensure that number of people on pontoon does not exceed maximum allowed | number of people on water based installation to be limited | person falling off intermediate start or stakeboat | Rescue with throwline or launch Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital | safety boats and first aid provision to be available in the start area and marshalls and umpires to be briefed on summoning help all stakeboat personnel and umpires to wear buoyancy aids/lifejackets Provide adequate first aid cover Provide somewhere warm for anyone suffering from cold | immersion in cold water | 1 | B | Low | X | X | X
3 | [9 empty] | #N/A
4 | [9 empty] | #N/A
5 | [9 empty] | #N/A
6 | [9 empty] | #N/A
7 | [9 empty] | #N/A
Local Environment
1 | Cyclists and Pedestrians using roads along side the course | Limitation of number of cyclists allowed to accompany each course, signage on the course to indicate the presence of a risk, coaches on cycles not permitted on the south bank | No cycling in boating areas | collision between cyclist and athlete or pedestrians on the northside or southside roads of the course | Provisions for first aid available on site | ensure that marshalls are properly briefed | Injury from collision | 2 | B | Low | X | X |  | x | x
1 | Cyclists and Pedestrians using roads along side the course | Only authorised cyclists allowed to accompany each race ??? signage on the course to indicate the presence of a risk, coaches on cycles not permitted on the south bank | No cycling in boating areas Monitor number of cyclists Brief officials and coaches | collision between cyclist and athlete or pedestrians on the northside or southside roads of the course | Administer first aid Evacuate to hospital if necessary | ensure that marshalls are properly briefed Provisions for first aid available on site | Injury from collision | 2 | B | Low | X | X |  | x | x
2 | cars using the south road for access to the start | signs to display to drivers that they should drive on the right | umpires to be briefed to restrict the number of cars used | Collision between cars | provision for first aid available o site | ensure that marshalls and umpires are properly briefed as to safety procedures | injury and vehicle damage | 3 | A | Low | x | x |  |  | x
2 | cars using the south road for access to the start | signs to display to drivers that they should drive on the right Umpires to restrict the number of cars used | access to be controlled to those with permits. Signs to be displayed to instruct re driving on the right | Collision between cars | Administer first aid Evacuate to hospital if necessary | ensure that marshalls are properly briefed Provisions for first aid available on site | injury and vehicle damage | 3 | A | Low | x | x |  |  | x
3 | congestion between cars and pedestrians in the finish tower area | cars in the finish tower area to be limited to those strictly necessary | volunteers to be properly briefed on use of cars and access | Collisions between cars and pedestrians | first aid available on site | proper briefing as to the summoning of first air | injury to individuals and athletes | 3 | B | Low | X | X |  |  | X
3 | congestion between cars and pedestrians in the finish tower area | cars in the finish tower area to be limited to those strictly necessary | volunteers to be properly briefed on use of cars and access | Collisions between cars and pedestrians | Administer first aid Evacuate to hospital if necessary | ensure that marshalls are properly briefed Provisions for first aid available on site | injury to individuals and athletes | 3 | B | Low | X | X |  |  | X
4 | Access to the pre-start area behind the start | Marshall to be present on the back yellow buoy to be used | briefing of bank marshal | Collision with cable in lane 7 for intermediate start | safety boat to be present at the start, | briefing of start marshalls on summoning support and first aid if necessary | minor damage to boat, possible immersion in cold water | 2 | C | Low | X | X |  |  | X
4 | Access to the pre-start area behind the start | yellow buoy to be used Marshal to direct crews | briefing of bank marshal Marshall to be present on the back | Collision with cable in lane 7 for intermediate start | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Provide working radios, ensure officials know how to use them and the correct radio procedure Provide sufficient safety cover Provide adequate first aid cover | minor damage to boat, possible immersion in cold water | 2 | C | Low | X | X |  |  | X
5 | Crews above start marshalling for racing | Umpire launch and safety launch in the start area | Briefing of umpires - umpires to collect the race and guide on to the start together with start zone supervisor | Collision in start zone | safety launch to be present in start area | umpires and marshalls to be briefed on how to summon first aid and safety boats | minor boat damage | 1 | C | Low | X | X | X
5 | Crews above start marshalling for racing | Crews to follow umpires' instructions | Briefing of umpires - umpires to collect the race and guide on to the start together with start zone supervisor | Collision in start zone | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Ensure that if a collision takes place on the water it is coordinated by Head of Control Commission and the Safety Coordinator marshalls and umpires to be briefed in summoning first aid and safety boat assistance safety boats and first aid facilities to be available at the start Umpire launch and safety launch in the start area Provide working radios, ensure officials know how to use them and the correct radio procedure Provide sufficient safety cover Provide adequate first aid cover | minor boat damage | 1 | C | Low | X | X | X
6 | stakeboat start pontoons | crews to be aware of the need to attach to pontoons in advance of the race, crews to be selected on ability, safety boats and marshalls and umpires in start area | briefing od coaches, marshalls and safety boats | Collision with stake boats whilst attempting to attach | safety boats and first aid facilities to be available at the start | marshalls and umpires to be briefed in summoning first aid and safety boat assistance | minor boat damage, immersion in cold water | 2 | D | Moderate | X | X | X
6 | stakeboat start pontoons | Crews to follow instructions Crews to be competent in attaching to stake boats | briefing of coaches, marshalls and safety boats crews to be aware of the need to attach to pontoons in advance of the race, crews to be selected on ability, safety boats and marshalls and umpires in start area | Collision with stake boats whilst attempting to attach | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | Ensure that if a collision takes place on the water it is coordinated by Head of Control Commission and the Safety Coordinator marshalls and umpires to be briefed in summoning first aid and safety boat assistance safety boats and first aid facilities to be available at the start Umpire launch and safety launch in the start area Provide working radios, ensure officials know how to use them and the correct radio procedure Provide sufficient safety cover Provide adequate first aid cover | minor boat damage, immersion in cold water | 2 | D | Moderate | X | X | X
7 | [9 empty] | #N/A
Going afloat and landing
1 | Congestion in Boating Area | Racing Every 5 minutes with only 6 boats to get onto the water in that time. Northbank landing stage to only be used for embarkation along with two northerly station in boating area, no cycling to be allowed I boating area. | Endure that race times are kept to, appropriately brief control commission umpires in respect of boating and ensure that umpire present on Country Park stage, ensure that NWSC signs re cycling are properly displayed | Collision in the Boating Area | Properly briefed and observant boating marshalls, coaches to assist with boating, marshalls to supervise the pushing out of all boats, marshalls to be equipped with throwlines | Ensure that if a collision takes place on the water it is coordinated by Head of Control Commission and the Safety Coordinator | Minor injury, cold water immersion, minor damage to boats | 1 | C | Low | X |  |  | X
1 | Congestion in Boating Area | Crews to use correct boating procedures Suspend boating if area becomes congested coaches to assist with boating, marshalls to supervise the pushing out of all boats | Ensure that race times are kept to, appropriately brief control commission umpires in respect of boating and ensure that umpire present on Country Park stage, ensure that NWSC signs re cycling are properly displayed Racing Every 5 minutes with only 6 boats to get onto the water in that time. Northbank landing stage to only be used for embarkation along with two northerly station in boating area, no cycling to be allowed I boating area. Brief crews Properly briefed and observant boating marshalls | Collision in the Boating Area | Rescue with launch or throwline Summon help from other launches Administer first aid Slowly warm anyone suffering from cold, if necessary take to hospital Recover boat Suspend racing until course is clear | marshalls to be equipped with throwlines Provide working radios, ensure officials know how to use them and the correct radio procedure Provide sufficient safety cover Provide adequate first aid cover | Minor injury, cold water immersion, minor damage to boats | 1 | C | Low | X |  |  | X
2 | [9 empty] | #N/A
3 | [9 empty] | #N/A
4 | [9 empty] | #N/A
5 | [9 empty] | #N/A
6 | [9 empty] | #N/A
7 | [9 empty] | #N/A
handling boats on land
1 | Collision between boats being carried to boating | circulation pattern to be implemented and supervisied by umpires and other regatta officials within the area | Umpires and other regatta officials to ensure compliance. Team managers to be briefed | Collision between boats | All team managers to be briefed as to the circulation pattern for boating and instructed to inform their crews. | crews transgressing to be reminded and incidents raised with team managers if necessary. Specific instructions to be included in future years, with the threat of penalty should these instructions not be complied with | Damage to boats or physical harm to individuals | 2 | C | Low | X | X |  | X | X
2 | [9 empty] | #N/A
3 | [9 empty] | #N/A
4 | [9 empty] | #N/A
5 | [9 empty] | #N/A
6 | [9 empty] | #N/A
7 | [9 empty] | #N/A
Faulty, incorrectly set and poorly maintained equipment
1 | Failure of Umpires Launch | All launches to be served by centre, five launches to be available and suppleant ??? to be followed so another launch can take a race if necessary | briefing for launch drivers on suppleant | Umpires launch breaking down during a race | Other launches in suppleant to take over, umpire to radio to confirm issue and race controller to manage the on water traffic | Proper briefing and communication between all parties |  | 1 | C | Low | X | X |  |  | X
1 | Failure of Umpires Launch | All launches to be served by centre, five launches to be available and suppleant ??? to be followed so another launch can take a race if necessary Check launches thoroughly at beginning of day Carry sufficient fuel | briefing for launch drivers on suppleant Provide check list for drivers Make sufficient fuel available | Umpires launch breaking down during a race | Other launches in suppleant to take over, umpire to radio to confirm issue and race controller to manage the on water traffic | Proper briefing and communication between all parties |  | 1 | C | Low | X | X |  |  | X
2 | [9 empty] | #N/A
3 | [9 empty] | #N/A
4 | [9 empty] | #N/A
5 | [9 empty] | #N/A
6 | [9 empty] | #N/A
7 | [9 empty] | #N/A
Pre-existing health conditions and low levels of fitness
1 | Pre-existing health conditions |  |  | Collapse or incapacitation of athlete during racing | Umpires briefed to contact safety/first aid and assist the athlete in getting treatment asap in coordination with safety provision and first aid | Ensure that umpires are properly briefed on first aid procedures | Injury or health implication for the athlete | 3 | C | Moderate | X | X | X |  | X
1 | Pre-existing health conditions | Encourage competitors to carry medication | Request to competitors to carry medication | Collapse or incapacitation of athlete during racing | Control Commission to assist athlete in obtaining first aid via radio Get person off the water Administer first aid Evacuate to hospital if necessary | Ensure that umpires are properly briefed on first aid procedures Umpires briefed to contact safety/first aid and assist the athlete in getting treatment asap in coordination with safety provision and first aid Have a procedure for getting the person off the water Provide adequate first aid cover Define and communicate evacuation procedure | Injury or health implication for the athlete | 3 | C | Moderate | X | X | X |  | X
2 | Pre-existing Health Conditions |  |  | Incapacitation of athlete prior or subsequent to boating (on land) | Control Commission to assist athlete in obtaining first aid via radio | Ensure that umpires are properly briefed on first aid procedures | Injury or health implication for the athlete | 3 | C | Moderate | x | x | x | x | x
2 | Pre-existing Health Conditions | Encourage competitors to carry medication | Request to competitors to carry medication | Incapacitation of athlete prior or subsequent to boating (on land) | Control Commission to assist athlete in obtaining first aid via radio Administer first aid Evacuate to hospital if necessary | Ensure that umpires are properly briefed on first aid procedures Umpires briefed to contact safety/first aid and assist the athlete in getting treatment asap in coordination with safety provision and first aid Provide adequate first aid cover Define and communicate evacuation procedure | Injury or health implication for the athlete | 3 | C | Moderate | x | x | x | x | x
3 | [9 empty] | #N/A
4 | [9 empty] | #N/A
5 | [9 empty] | #N/A
6 | [9 empty] | #N/A
7 | [9 empty] | #N/A
Other
1 | Continued radio traffic on other matters once an incident occurs | brief umpires and marshalls on appropriate procedures in emergencies (pan-pan) and appropriately briefed in communication protocol | umpires briefing | inability to communicate concerning an incident | Committee to be available by phone, umpires to be briefed | umpires briefing | delay in delating with an incidence | 1 | C | Low | X |  | X
1 | Continued radio traffic on other matters once an incident occurs | Check that radio users know the correct radio procedures to be used Check that radio users know emergency radio procedure | brief umpires and marshalls on appropriate procedures in emergencies (pan-pan and May-day) and appropriately briefed in communication protocol Provide cribsheet on communications for radio users | inability to communicate concerning an incident | Use mobile phones for essential non-emergency traffic | Brief umpires Committee to be available by phone, umpires to be briefed Provide list of mobile phone numbers | delay in delating with an incidence | 1 | C | Low | X |  | X
2 | [9 empty] | #N/A
3 | [9 empty] | #N/A
4 | [9 empty] | #N/A
5 | [9 empty] | #N/A
6 | [9 empty] | #N/A
7 | [9 empty] | #N/A
8 | [9 empty] | #N/A
9 | [9 empty] | #N/A
10 | [9 empty] | #N/A
11 | [9 empty] | #N/A
12 | [9 empty] | #N/A
13 | [9 empty] | #N/A
14 | [9 empty] | #N/A
Note on I2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is supposed to be the date of the risk assessment not the date of fthe event
Note on I5: 1 = Slight Injury or health effect that requires little or no treatment, and has no potential for time off rowing or training. OR Minor damage to equipment (<£100) 2 = Minor Injury or health effect that requires First Aid treatment or rest only and has a potential for a few days off rowing or training. OR Low damage repair costs (>£500) 3 = Moderate Injury or health effect that requires treatment beyond simple First Aid and potential for a week or so off rowing or training. OR High damage repair costs (>£1000) 4 = Major Injury or health effect that requires hospital treatment for more than one day and potential for a few weeks off rowing or training. OR Very high damage repair costs (loss of boat, 3rd party damage) 5 = Fatality or life threatening injury or health effect that could end a rowing career OR Major damage & major costs (loss of several boats, high 3rd party damage)
Note on J5: A = Highly improbable (has not been known to happen in rowing) B = Improbable (has been known to happen in rowing) C = Possible (could happen to about 1% of the competitors each decade) D = Probable (could happen to about 1% of the competitors each year) E = Highly probable (could happen to about 10% of the competitors each year)
Note on G13: Andrea: Provide first aid cover and facilities to warm those suffering from cold.
Note on D24: Worley: Make reference to the abandonment plan
Note on F27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a Barrier (reduces probability) and not a control (reduces severity). Think of retrieval, first aid and evacuation to hospital, as below
Note on D48: Worley: This is the same as the barrier. The acction to maintain barriers coulf be supervision by the CoRSA of a writtten notice or instruction.
Note on D96: Worley: Mayday is inclyded here - good

## Matrix
|  | People | Assets | Probability
|  |  |  | A | B | C | D | E
|  |  |  | Highly improbable (has not been known to happen in rowing) | Improbable (has been known to happen in rowing) | Possible (could happen to about 1% of the club's active members per decade) | Probable (could happen to about 1% of the club's active members per year) | Highly probable (could happen to about 10% of the club's active members per year)
Severity | 1 | Slight injury or health effect (Requires little or no treatment; no need to take time off rowing or training) | Minor damage to equipment (<£100) | Low | Low | Low | Low | Moderate
| 2 | Minor injury or health effect (Requires First Aid or rest; potentially a few days off rowing or training) | Damage repair costs low (£500) | Low | Low | Low | Moderate | Substantial
| 3 | Moderate injury or health effect (Requires treatment beyond simple First Aid; potentially a week or so off rowing or training) | High damage repair costs (>£1000) | Low | Low | Moderate | Substantial | Intolerable
| 4 | Major injury or health effect (Requires hospital treatment for more than one day; potentially a few weeks off rowing or training) | Very high damage repair costs (loss of boat, 3rd party damage) | Low | Moderate | Substantial | Intolerable | Intolerable
| 5 | Fatality or Life Threatening Injury or Health Effect (could end a rowing career or cause hospitalisation for a few months) | Major damage & major costs (loss of several boats, high 3rd party damage) | Moderate | Substantial | Intolerable | Intolerable | Intolerable
|  | Low | An acceptable level of risk. No additional barriers/controls are required. Start or continue the activity but check that the current barriers/controls remain effective.
|  | Moderate | An acceptable level of risk that should be reviewed. Implement additional barriers/controls to reduce the risk if the opportunity arises. Start or continue the activity with care.
|  | Substantial | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced.
|  | Intolerable | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced. Prohibit the activity if it is not possible to reduce the risk.

## Sheet1 (hidden)
1 | A | Phone to summon assistance | Map showing navigation rules in boathouse | X | Launch | Ensure that rowers are always accompanied by the coaching launch
2 | B | Navigation rules | Enforce procedure to carry mobile phone in waterproof carrier |  | Capsize drill | Ensure capsize drills are run at the start of each season as a minimum. Keep a record
3 | C | Cox, bow steer competence | Club registration of coxes and bow steers competence |  | Steering competence | Ensure rowers become approved steers by passing the steering assessment.
4 | D | Club rescue launch | Ensure club rescue launch and crew are on the water or available and ready to boat at all times |  | Coaching | Ensure that rowers are coached in the correct handling of less stable boats
5 | E
1A | Low
1B | Low
1C | Low
1D | Low
1E | Moderate
2A | Low
2B | Low
2C | Low
2D | Moderate
2E | Substantial
3A | Low
3B | Low
3C | Moderate
3D | Substantial
3E | Intolerable
4A | Low
4B | Moderate
4C | Substantial
4D | Intolerable
4E | Intolerable
5A | Moderate
5B | Substantial
5C | Intolerable
5D | Intolerable
5E | Intolerable

## Event Responsibilities
Event Committee | Event RSA | Safety Boat Drivers | Control Commission | other (specify)
Event to prepare safety instructions and brief coaches and athletes to read it | To monitor weather conditions in the lead up to the event | To coordinate cover with the RCC and the safety advisor concerning cover for the lake and communication plan in advance of safety briefing for umpires and marshalls | To ensure that there is no cycling in boating area | Hut in Boating Area - to issue numbers only in accordance with racing schedule and only up to a specified time before race to control number of boats on water
Event to prepare a circulation pattern to be communicated to all competitirs and coaches in advance of crews going afloat | To monitor weather conditions on the day of the event together with the Race Committee Chair |  | To brief crews on weather conditions and kit when going afloat if appropriate | NWSC: To ensure launches are serviced
Event to ensure correct equipment provided for each volunteer | To ensure that the correct signage has been displayed around the regatta course |  | To summon assistancce to incidents in the boating area | NWSC: To display the correct signage
To coordinate with centre to make sure planned provisions are put in place | Check equipment before use |  |  | Start Zone Supervisor: To summon assistance for an incident in the start area
To ensure breifing on appropriate radio protocol | Brief launc drivers |  |  | Umpires: To summon assistance to incidents within racing
To prepare a safety plan and circulate in advance of the event. | Ensure everyone is fully briefed on contingency planning
To display the safety plan
Ensure that there are sufficient marshalls and umpires
Ensure that there are sufficient launches available for the event and that there is a congency plan in event of breakdowns
Ensure the proper provision of first aid faciities
Ensure that communications are effective
Ensure that all volunteers are briefed on the abandonment plans and contingency planning and that communications are effective through briefing

## Colour key
Low | An acceptable level of risk. No additional barriers/controls are required. Start or continue the activity but check that the current barriers/controls remain effective.
Moderate | An acceptable level of risk that should be reviewed. Implement additional barriers/controls to reduce the risk if the opportunity arises. Start or continue the activity with care.
Substantial | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced.
Intolerable | An unacceptable level of risk. Improve the barriers/controls and allocate resources to reduce the risk. Do not start or continue the activity until the risk has been reduced. Prohibit the activity if it is not possible to reduce the risk.