## Sheet1
Task | Deadline | Person responsible | Status
Get permissions etc (e.g. local river authority, local authority for land use) | 10 months before
Decide entry fees | 4 months before
Poster | 4 months before
Order portaloos | 4 months before
Update website | 3 months before
Book First Aid | 3 months before
Book safety boats | 3 months before
Book Security | 3 months before
Book PA/megaphones | 3 months before
Book umpires' flags and bells | 3 months before
Order base quantity of pots/medals | 3 months before
Invite Umpires | 3 months before
Distribute poster | 3 months before
Set up BROE | 3 months before
Review and submit Risk Assessment | 8 weeks before
Review and set Race Instructions, safety information, maps etc and post on website | 8 weeks before
Bow Numbers - sort, count and order as required | 6 weeks before
Paper numbers with names of crews/events + pins | After entries close
Recruit Volunteers for the day | 4 weeks before
Remove weeds / obstructions from the course | 2 weeks before
Prepare and publish the Draw (website and email) | 1 week before
Briefing for helpers | Wednesday before
Sort numbers for registration | Thursday before
Buy food for catering | 2 days before
Put live results link on website | Day before
Tidy and clean boathouse | Day before
Check there's enough loo roll | Day before
Set up the boathouse and grounds for the day | Day before
Buoy the course | 6am race day
Put start and finish sign up | 7am race day
Update website with course records, lost property and thanks | Day after
Put everything away | Day after
Thank everyone | Day after
Process any refunds | Within 4 days
Upload results to BROE | Within 4 days
Capture learnings | Within 1 week